## Sheet1
Plan up until my deadline (15th June anticipated deadline)
Week Beginning
22nd May | Outline a plan on the key features required for this project
Log In Page (Priority)
Interactive Maps (Priority)
Chat Box (Priority)
Database (Priority)
Main objective for this week should be to create the database
Alongside this make sure that when a user signs up, data is added to the database
Followed by the information being displayed on the interactive maps (Templated already implemented)
29th May | Chat box to be implemented
Work on the report, extending and adding implementation stages
By this stage, I should have enough to talk about the different stages I have been through in the year
in regards to the project
5th June | Potentially add a directions feature from the users house to destination
Be able to add a 'find' feature for the user trying to organise a game
Have a 'market' feature for users to find a game and be able to alert the person that posted the game
Once a user had logged in, they should be allowed to change some features in their profile
Complete a draft for the report
12th June | To be finished with the main elements of the artefact (subject to adding additional features)
Be ready to submit a final report depending on the deadline given